## Report
[Project Title]
Earned Value Analysis Report
| Prepared By: | [Manager's Name] | [13 empty] | © 2012-2017 Vertex42 LLC
| Date: | [Report Date]
[42]
| For Period: | Week 7
Summary:
[Use this space to write a brief summary or to record specific observations or notes]
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01
1 | CANTEEN Re-visit drawing and BQ | 6720 | 5760 | 960
2 | CANTEEN FARMC and LOA | 640 |  | 640
3 | CANTEEN Kick Off Meeting | 4480 |  |  |  | 4480
4 | CANTEEN Work Schedule | 15680 |  |  |  | 15680
5 | CANTEEN Insurance | 8960 |  |  |  | 8960
6 | CANTEEN Mobilisation | 9600 |  |  |  | 9600
7 | CANTEEN Construction | 86400 |  |  |  | 34560 | 40320 | 11520
8 | CANTEEN Completion join inspection | 2240 | [5 empty] | 2240
9 | CANTEEN DLP end joint inspection | 2240 | [22 empty] | 2240
10 | CANTEEN CPC | 11200 | [5 empty] | 11200
11 | CANTEEN CMGD | 11200 | [22 empty] | 11200
12 | FINAL ACCOUNT | 11200 | [25 empty] | 11200
Insert new rows above this one
| Total Budgeted Cost | 170560 | 5760 | 1600 | 0 | 73280 | 40320 | 24960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13440 | 0 | 0 | 11200
|  | Cumulative Planned Value (PV) | 5760 | 7360 | 7360 | 80640 | 120960 | 145920 | 145920 | 145920 | 145920 | 145920 | 145920 | 145920 | 145920 | 145920 | 145920 | 145920 | 145920 | 145920 | 145920 | 145920 | 145920 | 145920 | 159360 | 159360 | 159360 | 170560
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 27760 | 58208 | 84976 | 111744 | 128832 | 145920 | 145920 | 146060 | 146200 | 147140 | 148080 | 149020 | 149960 | 150900 | 151840 | 152780 | 153720 | 154660 | 155600 | 156540 | 157480 | 158420 | 159360 | 159360 | 164960 | 170560
|  | Cumulative Earned Value (EV) | 28336 | 56672 | 81328 | 105984 | 120960 | 145920 | 145920 | 146032 | 146704 | 147376 | 148048 | 148720 | 149392 | 150064 | 150736 | 151408 | 152080 | 152752 | 153424 | 154096 | 154768 | 155440 | 159360 | 162720 | 166080 | 170560
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | 576 | -1536 | -3648 | -5760 | -7872 | 0 | 0 | -28 | 504 | 236 | -32 | -300 | -568 | -836 | -1104 | -1372 | -1640 | -1908 | -2176 | -2444 | -2712 | -2980 | 0 | 3360 | 1120 | 0
|  | Schedule Variance (SV = EV - PV) | 22576 | 49312 | 73968 | 25344 | 0 | 0 | 0 | 112 | 784 | 1456 | 2128 | 2800 | 3472 | 4144 | 4816 | 5488 | 6160 | 6832 | 7504 | 8176 | 8848 | 9520 | 0 | 3360 | 6720 | 0
|  | Cost Performance Index (CPI = EV/AC) | 1.0207 | 0.97361 | 0.95707 | 0.94845 | 0.9389 | 1 | 1 | 0.99981 | 1.0034 | 1.0016 | 0.99978 | 0.99799 | 0.99621 | 0.99446 | 0.99273 | 0.99102 | 0.98933 | 0.98766 | 0.98602 | 0.98439 | 0.98278 | 0.98119 | 1 | 1.0211 | 1.0068 | 1
|  | Schedule Performance Index (SPI = EV/PV) | 4.9194 | 7.7 | 11.05 | 1.3143 | 1 | 1 | 1 | 1.0008 | 1.0054 | 1.01 | 1.0146 | 1.0192 | 1.0238 | 1.0284 | 1.033 | 1.0376 | 1.0422 | 1.0468 | 1.0514 | 1.056 | 1.0606 | 1.0652 | 1 | 1.0211 | 1.0422 | 1
|  | Estimated Cost at Completion (EAC) | 167092.9418 | 175182.7442 | 178210.5371 | 179829.5652 | 181659.9365 | 170560 | 170560 | 170592.703 | 169974.043 | 170286.8744 | 170596.8659 | 170904.0559 | 171208.4824 | 171510.1823 | 171809.1922 | 172105.5479 | 172399.2846 | 172690.4368 | 172979.0385 | 173265.123 | 173548.7233 | 173829.8713 | 170560 | 167038.1121 | 169409.7881 | 170560
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
Cumulative Earned Value (EV)
WBS | Task Name | TBC | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01
1 | CANTEEN Re-visit drawing and BQ | 6720 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | CANTEEN FARMC and LOA | 640 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | CANTEEN Kick Off Meeting | 4480 | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | CANTEEN Work Schedule | 15680 | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5 | CANTEEN Insurance | 8960 | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | CANTEEN Mobilisation | 9600 | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | CANTEEN Construction | 86400 | 15% | 30% | 45% | 60% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | CANTEEN Completion join inspection | 2240 | 15% | 30% | 45% | 60% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | CANTEEN DLP end joint inspection | 2240 | [7 empty] | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 75% | 100% | 100% | 100% | 100%
10 | CANTEEN CPC | 11200 | 15% | 30% | 45% | 60% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | CANTEEN CMGD | 11200 | [8 empty] | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 100% | 100% | 100% | 100%
12 | FINAL ACCOUNT | 11200 | [8 empty] | 100%: 30%; 100%: 60%; 100%: 100%
|  | Cumulative EV | 28336 | 56672 | 81328 | 105984 | 120960 | 145920 | 145920 | 146032 | 146704 | 147376 | 148048 | 148720 | 149392 | 150064 | 150736 | 151408 | 152080 | 152752 | 153424 | 154096 | 154768 | 155440 | 159360 | 162720 | 166080 | 170560

## AC
Actual Cost Worksheet
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01
1 | CANTEEN Re-visit drawing and BQ |  | 2016-03-01: 3360; 2016-04-01: 3360
2 | CANTEEN FARMC and LOA |  | 2016-03-01: 320; 2016-04-01: 320
3 | CANTEEN Kick Off Meeting |  | 2016-03-01: 1120; 2016-04-01: 1120; 2016-05-01: 1120; 2016-06-01: 1120
4 | CANTEEN Work Schedule |  | 2016-03-01: 3920; 2016-04-01: 3920; 2016-05-01: 3920; 2016-06-01: 3920
5 | CANTEEN Insurance |  | 2016-03-01: 2240; 2016-04-01: 2240; 2016-05-01: 2240; 2016-06-01: 2240
6 | CANTEEN Mobilisation |  | 2016-03-01: 2400; 2016-04-01: 2400; 2016-05-01: 2400; 2016-06-01: 2400
7 | CANTEEN Construction |  | 2016-03-01: 14400; 2016-04-01: 14400; 2016-05-01: 14400; 2016-06-01: 14400; 2016-07-01: 14400; 2016-08-01: 14400
8 | CANTEEN Completion join inspection |  | 2016-04-01: 448; 2016-05-01: 448; 2016-06-01: 448; 2016-07-01: 448; 2016-08-01: 448
9 | CANTEEN DLP end joint inspection | [8 empty] | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
10 | CANTEEN CPC |  | 2016-04-01: 2240; 2016-05-01: 2240; 2016-06-01: 2240; 2016-07-01: 2240; 2016-08-01: 2240
11 | CANTEEN CMGD |  | 2016-12-01: 800; 2017-01-01: 800; 2017-02-01: 800; 2017-03-01: 800; 2017-04-01: 800; 2017-05-01: 800; 2017-06-01: 800; 2017-07-01: 800; 2017-08-01: 800; 2017-09-01: 800; 2017-10-01: 800; 2017-11-01: 800; 2017-12-01: 800; 2018-01-01: 800
12 | FINAL ACCOUNT |  | 2018-03-01: 5600; 2018-04-01: 5600
|  | Total Actual Cost | 27760 | 30448 | 26768 | 26768 | 17088 | 17088 | 0 | 140 | 140 | 940 | 940 | 940 | 940 | 940 | 940 | 940 | 940 | 940 | 940 | 940 | 940 | 940 | 940 | 0 | 5600 | 5600
|  | Cumulative Actual Cost (AC) | 27760 | 58208 | 84976 | 111744 | 128832 | 145920 | 145920 | 146060 | 146200 | 147140 | 148080 | 149020 | 149960 | 150900 | 151840 | 152780 | 153720 | 154660 | 155600 | 156540 | 157480 | 158420 | 159360 | 159360 | 164960 | 170560

## ©
Earned Value Management (EVM) Template
By Vertex42.com
http://www.vertex42.com/ExcelTemplates/critical-path-method.html
© 2012-2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
See License Agreement
http://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet. If necessary, you may hide it by right-clicking on the tab and selecting Hide.

## Sheet1
WBS | Task Name | TBC | % Wt. |  | Finish | Duration (Days) | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01
1 | CANTEEN Re-visit drawing and BQ | 6720 | 3.94% | 2016-03-24 | 2016-04-01 | 7 | 2016-03-01: 1.97%; 2016-04-01: 1.97%
2 | CANTEEN FARMC and LOA | 640 | 0.3752% | 2016-04-04 | 2016-04-04 | 1 | 2016-03-01: 0.1876%; 2016-04-01: 0.1876%
3 | CANTEEN Kick Off Meeting | 4480 | 2.627% | 2016-06-07 | 2016-06-08 | 2 | 2016-03-01: 0.6567%; 2016-04-01: 0.6567%; 2016-05-01: 0.6567%; 2016-06-01: 0.6567%
4 | CANTEEN Work Schedule | 15680 | 9.193% | 2016-06-07 | 2016-06-15 | 7 | 2016-03-01: 2.298%; 2016-04-01: 2.298%; 2016-05-01: 2.298%; 2016-06-01: 2.298%
5 | CANTEEN Insurance | 8960 | 5.253% | 2016-06-07 | 2016-06-24 | 14 | 2016-03-01: 1.313%; 2016-04-01: 1.313%; 2016-05-01: 1.313%; 2016-06-01: 1.313%
6 | CANTEEN Mobilisation | 9600 | 5.629% | 2016-06-07 | 2016-06-13 | 5 | 2016-03-01: 1.407%; 2016-04-01: 1.407%; 2016-05-01: 1.407%; 2016-06-01: 1.407%
7 | CANTEEN Construction | 86400 | 50.66% | 2016-06-07 | 2016-08-08 | 45 | 2016-03-01: 8.443%; 2016-04-01: 8.443%; 2016-05-01: 8.443%; 2016-06-01: 8.443%; 2016-07-01: 8.443%; 2016-08-01: 8.443%
8 | CANTEEN Completion join inspection | 2240 | 1.313% | 2016-08-16 | 2016-08-16 | 1 | 2016-03-01: 0.2189%; 2016-04-01: 0.2189%; 2016-05-01: 0.2189%; 2016-06-01: 0.2189%; 2016-07-01: 0.2189%; 2016-08-01: 0.2189%
9 | CANTEEN DLP end joint inspection | 2240 | 1.313% | 2018-01-10 | 2018-01-10 | 1 | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571% | 0.0571%
10 | CANTEEN CPC | 11200 | 6.567% | 2016-08-17 | 2016-08-23 | 5 | 2016-03-01: 1.094%; 2016-04-01: 1.094%; 2016-05-01: 1.094%; 2016-06-01: 1.094%; 2016-07-01: 1.094%; 2016-08-01: 1.094%
11 | CANTEEN CMGD | 11200 | 6.567% | 2018-01-11 | 2018-01-17 | 5 | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855% | 0.2855%
12 | FINAL ACCOUNT | 11200 | 6.567% | 2018-04-12 | 2018-04-18 | 5 | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526% | 0.2526%
| Total Amount | 170560 | 100%
|  | Monthly Progress |  |  |  |  | 18.18% | 18.18% | 16.03% | 16.03% | 10.35% | 10.35% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.5952% | 0.2526% | 0.2526% | 0.2526%
|  | Planned |  |  |  |  | 18.18% | 36.37% | 52.4% | 68.42% | 78.77% | 89.12% | 89.72% | 90.31% | 90.91% | 91.51% | 92.1% | 92.7% | 93.29% | 93.89% | 94.48% | 95.08% | 95.67% | 96.27% | 96.86% | 97.46% | 98.05% | 98.65% | 99.24% | 99.49% | 99.75% | 100%
|  | Actual Monthly |  |  |  |  | 1.97% | 2.345% | 0% | 39.59% | 16.89% | 24.77% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.88% | 0% | 0% | 6.567%
|  | Actual |  |  |  |  | 2016-03-01: 1.97%; 2016-04-01: 4.315%; 2016-05-01: 4.315%; 2016-06-01: 43.9%; 2016-07-01: 60.79%; 2016-08-01: 85.55%; 2016-09-01: 85.55%; 2016-10-01: 85.55%; 2016-11-01: 85.55%; 2016-12-01: 85.55%
|  | Task |  |  |  |  | 12 | 11.54 | 11.08 | 10.62 | 10.16 | 9.7 | 9.24 | 8.78 | 8.32 | 7.86 | 7.4 | 6.94 | 6.48 | 6.02 | 5.56 | 5.1 | 4.64 | 4.18 | 3.72 | 3.26 | 2.8 | 2.34 | 1.88 | 1.42 | 0.96 | 0
|  | Task Completed |  |  |  |  | 2016-03-01: 12; 2016-04-01: 10; 2016-05-01: 10; 2016-06-01: 7; 2016-07-01: 7; 2016-08-01: 4; 2016-09-01: 4; 2016-10-01: 4; 2016-11-01: 4; 2016-12-01: 4

## Sheet3
| 0.18184 | 0.36369 | 0.52395 | 0.68422 | 0.78773 | 0.89124 | 0.8972 | 0.90315 | 0.9091 | 0.91505 | 0.921 | 0.92695 | 0.93291 | 0.93886 | 0.94481 | 0.95076 | 0.95671 | 0.96266 | 0.96862 | 0.97457 | 0.98052 | 0.98647 | 0.99242 | 0.99495 | 0.99747 | 1
| 0.0197 | 0.023452 | 0 | 0.39587 | 0.16886 | 0.24765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.078799 | 0 | 0 | 0.065666
| 0.0197 | 0.043152 | 0.043152 | 0.43902 | 0.60788 | 0.85553 | 0.85553 | 0.85553 | 0.85553 | 0.85553
| 12 | 11.54 | 11.08 | 10.62 | 10.16 | 9.7 | 9.24 | 8.78 | 8.32 | 7.86 | 7.4 | 6.94 | 6.48 | 6.02 | 5.56 | 5.1 | 4.64 | 4.18 | 3.72 | 3.26 | 2.8 | 2.34 | 1.88 | 1.42 | 0.96 | 0
| 12 | 10 | 10 | 7 | 7 | 4 | 4 | 4 | 4 | 4
0.18184 | 0.36369 | 0.52395 | 0.68422 | 0.78773 | 0.89124 | 0.8972 | 0.90315 | 0.9091 | 0.91505 | 0.921 | 0.92695 | 0.93291 | 0.93886 | 0.94481 | 0.95076 | 0.95671 | 0.96266 | 0.96862 | 0.97457 | 0.98052 | 0.98647 | 0.99242 | 0.99495 | 0.99747 | 1
0.0197 | 0.043152 | 0.043152 | 0.43902 | 0.60788 | 0.85553 | 0.85553 | 0.85553 | 0.85553 | 0.85553
18.1843 | 36.3686 | 52.3953 | 68.4219 | 78.7732 | 89.1245 | 89.7196 | 90.3148 | 90.91 | 91.5051 | 92.1003 | 92.6955 | 93.2906 | 93.8858 | 94.481 | 95.0761 | 95.6713 | 96.2665 | 96.8616 | 97.4568 | 98.052 | 98.6471 | 99.2423 | 99.4949 | 99.7474 | 100
1.97 | 4.3152 | 4.3152 | 43.9024 | 60.788 | 85.5535 | 85.5535 | 85.5535 | 85.5535 | 85.5535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 11.54 | 11.08 | 10.62 | 10.16 | 9.7 | 9.24 | 8.78 | 8.32 | 7.86 | 7.4 | 6.94 | 6.48 | 6.02 | 5.56 | 5.1 | 4.64 | 4.18 | 3.72 | 3.26 | 2.8 | 2.34 | 1.88 | 1.42 | 0.96 | 0
12 | 10 | 10 | 7 | 7 | 4 | 4 | 4 | 4 | 4

## Sheet2
Budget | 170560
Cost | 145920
Cost Variance | 0
Remaining Cost | 24640