## Slide 1
Today: 25th December 2016 Data Date: 16th December 2016
KHTP Project Management Dashboard
TOTAL PROJECT PROGRESS TO-DATE
PROCUREMENT
LOGOUT
HOME
PROJECT COST UPDATE
2017
2018
2019
No of Projects
(ending 2017)
5
Nos
2020
2021
No of Projects
(ending 2017)
2
Nos
No of Projects
(ending 2017)
0
Nos
No of Projects
(ending 2017)
0
Nos
No of Projects
(ending 2017)
0
Nos
Chart: 
| 2017 | 2018 | 2019 | 2020 | 2021
Completed | 1 | 0 | 0 | 0 | 0
In Progress | 3 | 1 | 0 | 0 | 0
Not Started | 0 | 1 | 0 | 0 | 0
Delayed | 1 | 0 | 0 | 0 | 0
ending
ending
ending
ending
ending

## Slide 2
Today: 25th December 2016 Data Date: 16th December 2016
KHTP Project Management Dashboard
TOTAL PROJECT PROGRESS TO-DATE
PROCUREMENT
LOGOUT
HOME
PROJECT COST UPDATE
2017
2018
2019
No of Projects
(ending 2017)
5
Nos
2020
2021
No of Projects
(ending 2017)
2
Nos
No of Projects
(ending 2017)
0
Nos
No of Projects
(ending 2017)
0
Nos
No of Projects
(ending 2017)
0
Nos
Chart: 
| 2017 | 2018 | 2019 | 2020 | 2021
Completed | 1 | 0 | 0 | 0 | 0
In Progress | 3 | 1 | 0 | 0 | 0
Not Started | 0 | 1 | 0 | 0 | 0
Delayed | 1 | 0 | 0 | 0 | 0
ending
ending
ending
ending
ending
BC Building Cleaning

## Slide 3
Today: 25th December 2016 Data Date: 16th December 2016
KHTP Project Management Dashboard
OVERALL PROGRESS 2018
PROCUREMENT
LOGOUT
HOME
ACTUAL
35%
PLANNED
46%
VARIATION
-11
TREND
PROJECT COST UPDATE
Project Spent
to -date
400K
Ringgit Malaysia
Variation
Orders
100K
Ringgit Malaysia
Retention
Sum
500K
Ringgit Malaysia
Balance
6M
Ringgit Malaysia
Contingency
Sum
3M
Ringgit Malaysia
2018 PROJECTS - PERFORMANCE
PROJECTS |  | PERCENTAGE (%) |  |  |  |  |  | STATUS
 |  | Planned |  | Actual |  | Delay |  | 
Canteen Renovation |  | 89 |  | 89 |  | 0 |  | 
KTPC Office Renovation P2 |  | 47 |  | 30 |  | 17 |  | 
Completed
In Progress
Delay

## Slide 4
KHTP Project Management Dashboard
86%
PLANNED
ACTUAL
90%
86%
VARIANCE
4%
Progress
Chart: 
| 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979 | 43009 | 43040 | 43070 | 43101 | 43132 | 43160 | 43191
Planned | 0.18184 | 0.36369 | 0.52395 | 0.68422 | 0.78773 | 0.89124 | 0.8972 | 0.90315 | 0.9091 | 0.91505 | 0.921 | 0.92695 | 0.93291 | 0.93886 | 0.94481 | 0.95076 | 0.95671 | 0.96266 | 0.96862 | 0.97457 | 0.98052 | 0.98647 | 0.99242 | 0.99495 | 0.99747 | 1
Actual | 0.0197 | 0.043152 | 0.043152 | 0.43902 | 0.60788 | 0.85553 | 0.85553 | 0.85553 | 0.85553 | 0.85553
Planned vs Actual Progress
Task Burndown
Delayed Task
Name | Finish | Days Left | Variance | % Complete
Milestone Due
Name | Finish | Days Left | Variance | %Complete
Canteen Post Contract | 18-04-2018 | 471 | 0 | 88%
Canteen Work | 10-01-2018 | 373 | 0 | 98%
Canteen Certificate | 18-04-2018 | 471 | 0 | 33%
Cost Performance Index (CPI)
Schedule Performance Index (SPI)
1.00
1.00
Chart: 
| Budget | Cost | Cost Variance | Remaining Cost
 | 170560 | 145920 | 0 | 24640
Financial Analysis
Chart: 
| 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979 | 43009 | 43040 | 43070 | 43101 | 43132 | 43160 | 43191
Baseline | 12 | 11.54 | 11.08 | 10.62 | 10.16 | 9.7 | 9.24 | 8.78 | 8.32 | 7.86 | 7.4 | 6.94 | 6.48 | 6.02 | 5.56 | 5.1 | 4.64 | 4.18 | 3.72 | 3.26 | 2.8 | 2.34 | 1.88 | 1.42 | 0.96 | 0
Completed | 12 | 10 | 10 | 7 | 7 | 4 | 4 | 4 | 4 | 4
CANTEEN RENOVATION
PROCUREMENT
LOGOUT
HOME
Today: 25th December 2016 Data Date: 16th December 2016

## Slide 5
KHTP Project Management Dashboard
86%
PLANNED
ACTUAL
90%
86%
VARIANCE
4%
Progress
Chart: 
| 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979 | 43009 | 43040 | 43070 | 43101 | 43132 | 43160 | 43191
Planned | 0.18184 | 0.36369 | 0.52395 | 0.68422 | 0.78773 | 0.89124 | 0.8972 | 0.90315 | 0.9091 | 0.91505 | 0.921 | 0.92695 | 0.93291 | 0.93886 | 0.94481 | 0.95076 | 0.95671 | 0.96266 | 0.96862 | 0.97457 | 0.98052 | 0.98647 | 0.99242 | 0.99495 | 0.99747 | 1
Actual | 0.0197 | 0.043152 | 0.043152 | 0.43902 | 0.60788 | 0.85553 | 0.85553 | 0.85553 | 0.85553 | 0.85553
Planned vs Actual Progress
Task Burndown
Delayed Task
Name | Finish | Days Left | Variance | % Complete
Milestone Due
Name | Finish | Days Left | Variance | %Complete
Canteen Post Contract | 18-04-2018 | 471 | 0 | 88%
Canteen Work | 10-01-2018 | 373 | 0 | 98%
Canteen Certificate | 18-04-2018 | 471 | 0 | 33%
Cost Performance Index (CPI)
Schedule Performance Index (SPI)
1.00
1.00
Chart: 
| Budget | Cost | Cost Variance | Remaining Cost
 | 170560 | 145920 | 0 | 24640
Financial Analysis
Chart: 
| 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979 | 43009 | 43040 | 43070 | 43101 | 43132 | 43160 | 43191
Baseline | 12 | 11.54 | 11.08 | 10.62 | 10.16 | 9.7 | 9.24 | 8.78 | 8.32 | 7.86 | 7.4 | 6.94 | 6.48 | 6.02 | 5.56 | 5.1 | 4.64 | 4.18 | 3.72 | 3.26 | 2.8 | 2.34 | 1.88 | 1.42 | 0.96 | 0
Completed | 12 | 10 | 10 | 7 | 7 | 4 | 4 | 4 | 4 | 4
CANTEEN RENOVATION
PROCUREMENT
LOGOUT
HOME
Today: 25th December 2016 Data Date: 16th December 2016
Task | Baseline | Days Left | Variance | %Complete
Canteen Re-visit Drawing and BQ | 01-04-2016 | 0 | 0 | 88%
Canteen FARMC and LOA | 04-04-2018 | 0 | 0 | 98%
KPI